## Gov't Facilities (Op Services)
Government Facilites Operations Services
Facility Name & Description | Finding | Priority Rating | Person Responsible for Project | Recommendation | Actual Date Completed | Comment
Colllingdale Golf Clubhouse | Correct exterior public patio surface and pathway. | P1 | Operations Services Project Management Planning and Design | Replace patio surface with concrete and provide new pathway | 2024-10-01
Epic | Correct acccessible access to upper seating area of green ice rink | P1 | Operations Services Project Management Planning and Design | Install new wheelchair lift from ground floor to upper seating area | 2024-02-01
Epic | Correct accessible aseating for pool and blue ice rink bleacher areas | P1 | Operations Services Project Management Planning and Design | Create new wheelchair accessible dispresed seating area | 2024-02-01
Lee Martinez Farm | Correct gate to accessible pathway | P1 | Operations Services Project Management Planning and Design | Remove old gate and install new gate | 2024-07-02
City Park Nine Gold Clubhouse | Improve and correct access to restrooms | P1 | Operations Services Project Management Planning and Design | Renovate restrooms for ADA compliance | 2024-05-01
Gardens on Spring Creek | Imrpove door acess to single user restroom and exterior door | P1 | Operations Services Project Management Planning and Design | Install new power assist door operators wtih remote actuators | Repairs in progress | Restroom doors substantially complete. Working through exterior door locking issues.
Police Services (Timberline) | Correct accessible parking location and route to registration door | P1 | Operations Services Project Management Planning and Design | Relocate accessible parking, install new curb ramps and improve path to registration door | 2024-11-01
Gardens on Spring Creek | Improve accessible seating for outdoor great lawn performance area | P1 | Operations Services Project Management Planning and Design | Create new accessible seating areas | Construction planned spring 2025
Park Shop (Bryan Street) | Correct main entry vestibule door distance and access | P2 | Operations Services Project Management Planning and Design | Design new vestibule addition with accessible improvements | Construction planned spring 2025
Southbridge Golf Course Clubhouse | Correct counter height | P2 | Operations Services Project Management Planning and Design | Provide accessible counter area | Construction planned spring 2025
Lincoln Center | Improve existing South entrance ADA ramp and access in performance hall | P2 | Operations Services Project Management Planning and Design | Explore ramp relocation/reconfiguration and potential location for adding a wheelchair lift | Ramp construction planned spring 2025, interior access on-going
222 LaPorte | Improve staff accessibility by creating a new all gender/ADA restroom | P1 | Operations Services Project Management Planning and Design | Create new employee restroom | Designer selected.
700 Wood Street | Renovate main entry restrooms | P2 | Operations Services Project Management Planning and Design | Update existing restrooms to meet ADA and create an all gender restroom | Design in progress
300 LaPorte - City Hall | Correct ADA slopes at flagpole | P1 | Operations Services Project Management Planning and Design | Update existing flagpole access | Design in progress
Downtown Transit Center | Correct vestibule deficiencies | P1 | Operations Services Project Management Planning and Design | Address existing ADA deficiencies | Design in progress
Foothills Activity Center | Provide a new ADA ramp in parking deck to allow more egress flexibility | P1 | Operations Services Project Management Planning and Design | Improve ADA access to Foothills Mall parking deck elevators for residents who have to utilize emergency egress from upper floor of FAC into parking deck | Design in progress
Various ADA Restrooms | Improve minor restroom deficiencies | P1 | Operations Services Project Management Planning and Design | Address missing grab bars, paper towel heights, adding baby diaper changing stations, etc. at eight existing restroom. | Design in progress
Note on C3: Jan Reece: Definitions: Priority 1 is critical as barrier prohibits person with disability from utilizing program or service Priority 2 is serious as there are deficiencies that effectually inhibit a person from utilizing facility independently Priority 3 is moderate as deficiency affects the convenience of accessibility and Priority 4 is minor non-urgent deficiency that would be required to meet the new construction standards

## Natural Areas
Natural Areas Department
Facility Description | Finding | Priority Rating | Person Responsible For Project | Recommendation | Actual Date Completed | Comment
Arapaho Bend | Restripe existing parking spot to include van accessible parking space | P3 | Natural Areas - Built Infrastructure | Re-stripe the existing space to account for the minimum width for van accessible parking | Design in progress
Bobcat Ridge | Restripe existing parking spot to include van accessible parking space | P3 | Natural Areas - Built Infrastructure | Re-stripe the existing space to account for the minimum width for van accessible parking | Design in progress
Bobcat Ridge | Lower/replace emergency call box | P2 | Natural Areas - Built Infrastructure | Lower the height of the emergency call box | In progress
Cathry Fromme - S Shields | Restripe existing parking spot to include van accessible parking space | P3 | Natural Areas - Built Infrastructure | Re-stripe the existing space to account for the minimum width for van accessible parking | Design in progress
Coyote Ridge | Restripe existing parking spot to include van accessible parking space | P2 | Natural Areas - Built Infrastructure | Re-stripe the existing space to account for the minimum width for van accessible parking | Design in progress
Fossil Creek Reservoir | Install/raise sign designating accessible parking space with ISA | P3 | Natural Areas - Built Infrastructure | Raise the sign to the correct height | Design in progress
Gateway | Restripe existing parking spot to include van accessible parking space | P1 | Natural Areas - Built Infrastructure | Re-stripe the existing space to account for the minimum width for van accessible parking and adjust the height of the signs | Design in progress
Gateway | Adjust height of brochure boxes | P3 | Natural Areas - Built Infrastructure | Replace and adjust height of the brochure boxes | 2024-02-24
Gustav Swanson | Restripe existing parking spot to include van accessible parking space | P2 | Natural Areas - Built Infrastructure | Re-stripe the existing space to account for the minimum width | Design in progress
Maxwell | Restripe existing parking spot to include van accessible parking space | P2 | Natural Areas - Built Infrastructure | Re-stripe the existing space to account for the minimum width for van accessible parking and adjust the height of the signs | Design in progress
North Shields Pond | Restripe existing parking spot to include van accessible parking space | P2 | Natural Areas - Built Infrastructure | Re-stripe the existing space to account for the minimum width for van accessible parking and adjust the height of the signs | Design in progress
Pineridge | Restripe existing parking spot to include van accessible parking space | P2 | Natural Areas - Built Infrastructure | Re-stripe the existing space to account for the minimum width for van accessible parking | Design in progress
Reservoir Ridge | Restripe existing parking spot to include van accessible parking space | P2 | Natural Areas - Built Infrastructure | Re-stripe the existing space to account for the minimum width for van accessible parking and adjust the height of the signs | Design in progress
Riverbend Ponds | Restripe existing parking spot to include van accessible parking space | P2 | Natural Areas - Built Infrastructure | Re-stripe the existing space to account for the minimum width for van accessible parking and adjust the height of the signs | Design in progress
Soapstone | Adjust height of brochure boxes | P3 | Natural Areas - Built Infrastructure | Replace and adjust height of the brochure boxes | 2024-02-25

## Parks
Parks
Facility Description | Finding | Priority Rating | Person Responsible For Project | Recommendation | Actual Date Completed | Comment
Westfield Park | Correct changes in level/openings for accessible route | P3 | Park Planning and Development | Renovated courts and entry | 2024-07-02
Overland Park | Repair to accessible route | P1 | Park Planning and Development | Repaired pedestrian bridge over stormwater channel | 2024-06-15
Spring Creek Trail - Wallenberg Spur Bridge | Improve accessible route entry | na | Park Planning and Development | Renovate trail entry and pedestrian bridge | 2024-09-30
Rogers Park | Correct ADA ramps in parking lot |  | Park Planning and Development | Rebuilt ramps | 2024-11-01
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Matt Pflieger please review and add any other 2024 items from IRP

## Transfort
Transfort
Facility Description | Finding | Priority Rating | Person Responsible For Project | Recommendation | Actual Date Completed | Comment
DTC phase I completed 2024 (walkway pavers replaced, ramp to front door replaced), DTC phase II in 2025 (islands and connecting sidewalks due for replacement)
bus stop improvements (over 1M in funding secured for this, currently at 92% of Transfort jurisdiction stops ADA accessible)
ADA signage redesign on board buses in progress
ADA audio audit in progress for called stops and route identification